## Slide 1: Activity on node
Slides based on example at
http://hafeezrm.hubpages.com/hub/CASE-STUDY---Probability-in-PERT#

## Slide 2: The project
In the following example, the ‘project’ involves the construction of a yacht.
This example uses multiple predictions of activity duration – hence 3PE is used to calculate the new duration.
If only, one duration is given, then use that instead

## Slide 3: The activities
Prerequisite activity
Activity
optimistic | most likely | pessimistic

## Slide 4: Calculating 3PE
3PE = a + 4m + b
6

## Slide 5: Node sections
EARLIEST START TIME | ID NUM [optional] | EARLIEST FINISH TIME
FLOAT/SLACK TIME | DESCRIPTION [optional] | TOTAL FLOAT/SLACK TIME
LATEST START TIME | DURATION | LATEST FINISH TIME

## Slide 6
 | 1 | 
 | 2 | 
 | 3 | 
 | 5 | 
 | 6 | 
 | 4 | 
 | 7 | 
 | 8 | 
 | [9] | 
Draw each activity as a node
Connect each node to its pre-req activity

## Slide 7
 | 1 | 
 | 6 | 
 | 2 | 
 | 5 | 
 | 3 | 
 | 6 | 
 | 5 | 
 | 3 | 
 | 6 | 
 | 2 | 
 | 4 | 
 | 8 | 
 | 7 | 
 | 9 | 
 | 8 | 
 | 6 | 
 | [9] | 
Add durations for each node

## Slide 8
0 | 1 | 6
 | 6 | 
6 | 2 | 11
 | 5 | 
6 | 3 | 12
 | 6 | 
12 | 5 | 15
 | 3 | 
12 | 6 | 14
 | 2 | 
11 | 4 | 19
 | 8 | 
19 | 7 | 28
 | 9 | 
14 | 8 | 20
 | 6 | 
28 | [9] | 
Calculate ES and EF times
Start from first node and proceed right
Note that some references start the activity on the following day
Has two incoming activities, so choose larger value
+

## Slide 9
0 | 1 | 6
0 | 6 | 6
6 | 2 | 11
6 | 5 | 11
6 | 3 | 12
10 | 6 | 16
12 | 5 | 15
16 | 3 | 19
12 | 6 | 14
20 | 2 | 22
11 | 4 | 19
11 | 8 | 19
19 | 7 | 28
19 | 9 | 28
14 | 8 | 20
22 | 6 | 28
28 | [9] | 
Calculate LF and LS times
Start from end node and work backwards
Has two incoming activities, so choose smaller value
—

## Slide 10
0 | 1 | 6
 |  | 0
0 | 6 | 6
6 | 2 | 11
 |  | 0
6 | 5 | 11
6 | 3 | 12
 |  | 4
10 | 6 | 16
12 | 5 | 15
 |  | 4
16 | 3 | 19
12 | 6 | 14
 |  | 8
20 | 2 | 22
11 | 4 | 19
 |  | 0
11 | 8 | 19
19 | 7 | 28
 |  | 0
19 | 9 | 28
14 | 8 | 20
 |  | 8
22 | 6 | 28
28 | [9] | 
Calculate Total float TF = LS – ES = LF – EF

## Slide 11
0 | 1 | 6
0 |  | 0
0 | 6 | 6
6 | 2 | 11
0 |  | 0
6 | 5 | 11
6 | 3 | 12
0 |  | 4
10 | 6 | 16
12 | 5 | 15
4 |  | 4
16 | 3 | 19
12 | 6 | 14
0 |  | 8
20 | 2 | 22
11 | 4 | 19
0 |  | 0
11 | 8 | 19
19 | 7 | 28
0 |  | 0
19 | 9 | 28
14 | 8 | 20
8 |  | 8
22 | 6 | 28
28 | [9] | 
Calculate Free float (start to finish) FF = Earliest succeeding activity ES – activity’s EF
[Note there is more than one way to calculate FF – this is probably the easiest]